## Sheet1
Langley Fitzurse Draft Premises Plan
2018-11-09
Maintenance Requirements
| Status | Project | 2018/19 | 2019/20 | 2018/19 Estimate | 2019/20 Estimate | Comments
1 | Ongoing | Hercules carpet |  | Yes |  | 1000 | Moved to 2019/20- cleaned so can last
2 | Complete | Chameleon Redecoration |  |  |  |  | Completed Summer 2018
3 | Complete | Staff Room Redecoration |  |  |  |  | Completed Summer 2018
4 | Ongoing | Gazebo Roof Repair | Yes |  | 2100 |  | Will be completed once the branches are removed. Planning permission next few weeks
5 | Ongoing | Playground Surface Repair (tree roots etc) | Yes |  |  |  | Possible minor repairs and cleaning of drainage areas by the trees- requires monitoring
6 | NEW | Wet pore service by wooden play area |  |  |  |  | Work group to use degreaser. Wooden area still inoperative | Lizzy to discuss with Simon. Work group could clean surface
7 | Ongoing | EYFS Shelter drainage channels | Yes |  |  |  | Hoping to incorporate into annual gutter and valley cleaning | Awaiting quote
8 | Complete | Pegasus / Chameleon windows |  |  |  |  | Complete Spring 2018
9 | Ongoing | Head's office redecoration |  | Yes |  | 500 | Low priority | Roll into next year
10 | Ongoing | Admin office redecoration |  | Yes |  | 500 | Medium priority. | Roll into next year
11 | Ongoing | Roundhouse door replacement |  |  |  | 2800 | LA may do this. Beyond 2020. Storage area only currently | Continue to monitor on H&S walk round and upline of issue. LM to check with the LA
12 | Ongoing | Ceiling - Chameleon - awaiting feedback |  |  |  |  | Sagging ceiling noted on building survey. Desirable work next 3-5 years.
13 | Ongoing | Cherry Hall Bolier Room Door - rotten |  | Yes |  | 900 | LA will do this but it will by 20/21 earliest | Lizzy to request update from LA
14 | Ongoing | General roof work - as flagged 16/3 |  |  |  |  | Some completed April 2018. New leak in Chameleon - roof vent? Monitor in next few weeks
15 | Ongoing | Missing ceiling in cleaning cupboard |  | Yes |  | 200 | Not essential but good to have
16 | Ongoing | Playground blocked strip gulley |  |  | 500 |  | Monitor on H&S. Viewed 9/11.
17 | Ongoing | Improved door security between foyer and classrooms |  |  |  |  | Awaiting Richard's view
18 | Complete | Replace side gate by kitchen |  |  |  |  | Completed April 2018. Including improved fnecing by the bins
19 | NEW | Floor in old school entrance |  |  |  | 300 | Replacement 2019/20
20 | NEW | Cherry Hall - paintwork on kitchen wall and other touch up work | Yes |  |  | 500 | Estimated
|  | Total |  |  | 2600 | 6700
Last LA survey report 2017. Next one expected approx 2020.
Current Aspirational Ideas
| Status | Project | Priority | When |  | Estimate | Comments
1 | Ongoing | Mezzanine in Chameleon for IT suite / extra learning | Low |  |  | 0
2 | Ongoing | Playground surface - wholesale change inc astro turf | High |  |  | 0 | In Simon Rahn's project. May not be able to use sports grant
3 | Ongoing | Additional Classroom and or nursery | Low |  |  | 0
4 | Ongoing | Reconfigure entrance foyer for added security | Low |  |  | 0
5 | Ongoing | Parking | High |  |  |  | In progress with the Parish Council - there will need to be fund raising. Total cost £30k
6 | NEW | Sensory Room in Round House | Low |  |  | 0 | Consider door repair above.
|  | Total |  |  |  | 0
|  | Review of parent wish list - note March 2016 | Comments
|  | Parking - see above | In current aspirations
|  | Library needs to be more secluded | Decide if move to aspirations
|  | Review of staff wish list | Comments
|  | Lockers and storage for cloakrooms | Decide if move to aspirations
|  | Better playground surface | See above
Last Major Redecoration Work
|  | Classroom 1 (Herclules 2018) Pratten Classroom | Redecorated Summer 2013
|  | Classroom 2 (Pegasus 2018-2019) | Redecorated Summer 2013
|  | Classroom 3 L shaped (Chameleon 2018/19) | Redecorated Summer 2017
|  | Classroom 4 - front classroom (Pheonix) | Redecorated Summer 2018
|  | Cherry Hall | Redecorated Oct 2011
|  | Foyer | Redecorated 2010
|  | Head's Office | 2011-08-01
|  | Main Kitchen | 2014-05-01
|  | Childrens Toilets | 2009
|  | Old School Entrance | 2015
|  | Children's kitchen | 2015-02-01
|  | Staff Room | 1905-07-10
|  | Cloakroom between rooms 1-2 | Summer 2013
|  | Cloakroom between rooms 3&4 | 2012-10-01
|  | Finance | 2013-05-01
|  | Upstairs resources room | 2009-08-01
|  | Admin Office | Pre 2010