## Sheet1
Langely Fitzurse Risk Register |  | 2020-05-16
Risk | Impact | Probability | Mitigation | Owner
OFSTED find serious issue to reduce LF rating below good: | VH | 0.2 | Safeguarding - see below (HT/CS); Prevent - further audit in 2019, potentially as a swap with Lacock to increase independence (JK); Governance - clear SIP, governance matrix and active governor action plans (DB); Learning - see below (S&P) | See inside
2018/19 intake below 9 - resultant in class and staff streamlining | H | 0.3 | Social media presence continued Christmas card to open day attendees Marketing to New Builds - other show rooms Achieve "Good" OFSTED | LH/LP LH AS HT
Staff member leaves | M | 0.2 | Good induction of new staff / up to date job descriptions | HT
Safeguarding issue | VH | 0.1 | Thorough audit of process / documentation, with follow up actions handled promptly. Reciprocal audit with Lacock | CS / HT
Financial Impropriety | H | 0.1 | Process audit of purchasing, cash handling and credit card payments processes Regular review of accounts at L&R | IS
Learning in below national expectation | VH | 0.5 | By Jan/Feb: 1) Comprehensive and accurate attainment and progress data collected and analysed regularly, and used by staff to drive action; 2) Clear progress forecasting by all staff; 3) Documented intervention co-working between class teachers and subject / area leads to improve individual performances; 4) Effective and transparent use of pupil premium funds; | 1) JO 2) HT 3&4) HT/Link govs
New school opening in Birds Marsh 2021 | H | 0.95 | Be full and delivering excellent results by that date | DB
Improved since last issue
Same
Worse

## Sheet2
Risk | Impact | Probability | Mitigation | Owner
S&P Risks
OFSTED find serious issue to reduce LF rating below good: | VH | 0.2 | Safeguarding - see below (HT/CS); Prevent - further audit in 2019, potentially as a swap with Lacock to increase independence (JK); Governance - clear SIP, governance matrix and active governor action plans (DB); Learning - see below (S&P) | See inside
Learning in below national expectation | VH | 0.5 | By Jan/Feb: 1) Comprehensive and accurate attainment and progress data collected and analysed regularly, and used by staff to drive action; 2) Clear progress forecasting by all staff; 3) Documented intervention co-working between class teachers and subject / area leads to improve individual performances; 4) Effective and transparent use of pupil premium funds; | 1) JO 2) HT 3&4) HT/Link govs
L&R Risks
2020/2021 Intake Low - resultant in class and staff streamlining | L | 0.3 | Social media presence continued Christmas card to open day attendees Marketing to New Builds - other show rooms Achieve "Good" OFSTED | LH/LP LH AS HT
Staff member leaves | M | 0.2 | Good induction of new staff / up to date job descriptions | HT
Safeguarding issue | VH | 0.1 | Thorough audit of process / documentation, with follow up actions handled promptly. Reciprocal audit with Lacock | CS / HT
Financial Impropriety | H | 0.1 | Process audit of purchasing, cash handling and credit card payments processes Regular review of accounts at L&R | IS
New school opening in Birds Marsh 2021 results in reduced number on roll | H | 0.95 | Be full and delivering excellent results by that date | DB
Full time headteacher unaffordable | M | 0.5 | Partner/Federate with similar local school. Progress with hard federation, making shared head a permanent role. | DB
Failure to maintain school results in damage requiring extensive repair | M | 0.1 | Continue to conduct premises support, governor assigned to role backed up by finance officer. Allocate sufficient funds to maintenance | LM
Roundhouse falls into disrepair | L | 0.2 | H&S issue prevents building being used currently, lack of repair could lead to the building needing to be demolished or repaired at great cost | SR
PAN unachievable due to current layout of classrooms | L | 0.1 | Inability to meet theoretical PAN due to one classroom limiting size of year (?). Mitigation is to pursue increased capacity using additional accommodation on site. | DB
COVID-19 causes loss of resources or causes financial impact | VH | 0.9 | Follow government advice on making the school COVID-19 Secure and implement social distancing, cleaning and hygiene practises. Mitigate transmission risk where distancing is not possible. | KW
Further consequences of COVID - Failure of controls, failure to manage children who cannot come in (vulnerable etc), keeping in touch etc | H | 0.5 | One the controls are implem,ented and the first calsses return the staff will review the processes and controls and adapt as required. Advice will be updated as the LA and Government update the guidance. | KW
Failure of security leads to loss of assets or information | M | 0.1 | Implement adequate security controls and keep under regular review. | KW
Failure to protect personal information leads to breach and loss of trust | M | 0.1 | Data protection policies are in place and under constant review. | HS/KW
Poor SIAMS inspection results in school becoming less apealing to local community | L | 0.2 | Christian distinctiveness panel actively working with all governors and school staff to achieve best results fotr the school in the upcoming assessment. | HS/DB
Federeation fails to form or deliver intended benfits | M | 0.1 | Federation process is being overseen by the diosis and the local authority. A federation working group has been set up to manage the transistion to the new governing body. | DB/ES/HS/KW