## Sheet1
Langely Fitzurse Risk Register |  | 2018-11-24
Risk | Impact | Probability | Mitigation | Owner
OFSTED find serious issue to reduce LF rating below good: | VH | 0.2 | Safeguarding - see below (HT/CS); Prevent - further audit in 2019, potentially as a swap with Lacock to increase independence (JK); Governance - clear SIP, governance matrix and active governor action plans (DB); Learning - see below (S&P) | See inside
2018/19 intake below 9 - resultant in class and staff streamlining | H | 0.3 | Social media presence continued Christmas card to open day attendees Marketing to New Builds - other show rooms Achieve "Good" OFSTED | LH/LP LH AS HT
Staff member leaves | M | 0.2 | Good induction of new staff / up to date job descriptions | HT
Safeguarding issue | VH | 0.1 | Thorough audit of process / documentation, with follow up actions handled promptly. Reciprocal audit with Lacock | CS / HT
Financial Impropriety | H | 0.1 | Process audit of purchasing, cash handling and credit card payments processes Regular review of accounts at L&R | IS
Learning in below national expectation | VH | 0.5 | By Jan/Feb: 1) Comprehensive and accurate attainment and progress data collected and analysed regularly, and used by staff to drive action; 2) Clear progress forecasting by all staff; 3) Documented intervention co-working between class teachers and subject / area leads to improve individual performances; 4) Effective and transparent use of pupil premium funds; | 1) JO 2) HT 3&4) HT/Link govs
New school opening in Birds Marsh 2021 | H | 0.95 | Be full and delivering excellent results by that date | DB
Improved since last issue
Same
Worse