## Sheet1
Langley Fitzurse Draft Premises Plan
|  | Maintenance Requirements | 06th Dec
| Status | Project | 2019/20 | 2020/2021 | 2019/20 Estimate | 2020/2021 | 2021/22 Estimate | 2021/22 | Comments
1 | Ongoing | Hercules carpet |  | Yes |  | 1000 |  |  | Moved to 2020/21- cleaned so can last
2 | Ongoing | Hercules needs redecoration at same time as carpet replacement |  | Yes |  | 910
3 | Ongoing | Pegasus needs redecoration (classroom 002) |  | Yes |  | 840
4 | Ongoing | Head's office redecoration |  |  |  |  | 500 |  | Low priority
5 | Ongoing | Roundhouse door replacement |  | Yes |  | 2800 |  |  | LA consider this neglect on our behalf, therefore the school to carry cost.
6 | Ongoing | Ceiling - Chameleon - awaiting feedback | [6 empty] | Sagging ceiling noted on building survey. Desirable work next 3-5 years.
7 | Ongoing | Missing ceiling tile in cleaning cupboard |  | Yes |  | 200 |  |  | Not essential but good to have, plus other odd tiles elsewhere need replacing
8 | Ongoing | Improved door security between foyer and classrooms |  |  |  |  | £20,000 |  | This is to cover the cost of the new access via the admin office.
9 | NEW | 2 x Playground Gates and Increased height on fencing |  | Yes |  | 2000 |  |  | LA to do this work.
10 | Ongoing | Floor in old school entrance |  | Yes |  | 300 |  |  | Replacement 2020/21 arrange same time as Hercules carpet
11 | Ongoing | Cherry Hall - paintwork on kitchen wall and other touch up work |  |  |  |  | 2300 |  | Estimated complete redecoration
12 | NEW | Lockers / storage area | Yes |  |  |  | 500 |  | Lizzy to get quote. Quote recd for troughs NFA for now
13 | NEW | Wood Protection for Pratten Building |  |  |  |  | 3000 | 3000
14 | NEW | Wood Proctection for Adventure Kingdom |  |  |  |  | 200 | 200
16 | Monitor | Pluto Damp , check downpipe during heavy rain for effectivness
17 | Monitor | Classroom 003, Damp patch above filing cabinet
18 | Monitor | Classroom 004 Water runs down wall during heavy rain
19 | New | Foyer redecoration |  |  |  | Yes | 2370
20 | New | Gazebo wood protection (roof replaced 2019/20)
21 | New | Remove play train as repairs no longer viable
|  | Total |  |  | 0 | 8050 | 8870 | 3200
Current Aspirational Ideas
| Status | Project | Priority | When |  |  |  | Estimate | Comments
1 | Ongoing | Mezzanine in Chameleon for IT suite / extra learning | Low |  |  |  |  | 0
3 | Ongoing | Additional Classroom and or nursery | Low |  |  |  |  | 0
4 | Ongoing | Reconfigure entrance foyer for added security | Medium | 2020-2021 |  | 20000 |  | 0
5 | Ongoing | Library needs to be more secluded | [5 empty] | 0 | Consider door repair above.
6 | NEW | Round House complete renovtion to provide calm space | Low
7 | NEW | Bathroom needs secondary glazing |  |  |  | TBC
8 | NEW | Remove Bath and replace with kitchen cupboards and w/tops |  |  |  | TBC |  | 0
9 | NEW | Resources room needs Secondary glazing
10 | NEW | Meeting room needs secondary glazing
11 | NEW | Staff room needs secondary glazing
12 | New | Build additional outside space to provide extra classrooms | Medium | 2020-2021 | 12000
|  | Review of staff wish list | Comments
|  | Lockers and storage for cloakrooms | Decide if move to aspirations
Date of most recent LA Buildings Condition Survey - Sept 2017. Next one due 2020
Last Major Redecoration Work
|  | Classroom 001 Pratten Building (Hercules 2019/20 | Redecorated Summer 2013
|  | Classroom 002 Pratten Building (Pegasus 2019/20) | Redecorated Summer 2013
|  | Classroom 003 L shaped (Chameleon 2019/20) | Redecorated Summer 2017
|  | Classroom 004 - front classroom (Pheonix 2019/20) | Redecorated Summer 2018
|  | Cherry Hall | Redecorated Oct 2011
|  | Foyer | Redecorated 2010
|  | Head's Office | 2011-08-01
|  | Main Kitchen | 2014-05-01
|  | Childrens Toilets | 2009
|  | Old School Entrance | 2015
|  | Children's kitchen | 2015-02-01
|  | Staff Room | 2018-05-01
|  | Cloakroom between classrooms 001-002 | Summer 2013
|  | Cloakroom between rooms 003 & 004 | 2012-10-01
|  | Finance | 2013-05-01
|  | Upstairs resources room | 2009-08-01
|  | Admin Office | 2019-10-01
Completed projects 2019/20 financial year
|  | Admin office redecoration | 2019-10-01
|  | Cherry Hall Bolier Room Door - rotten | 2019-08-01
|  | EYFS Shelter drainage channels | 2019-09-01
|  | Playground Surface Repair (tree roots etc) and surface gully | 2019-10-01
|  | Priate boathouse platform | 2019-10-01
|  | Slide to replace pole in advneture kingdom. | 2019-09-01
|  | Small window high up front of school building | 2019-11-01
|  | Wet pour jetwash service by wooden play area | 2019-09-01