**Langley Fitzurse CE Primary School**

**School Improvement Plan 2019 – 2020**

**Vision:**

At Langley Fitzurse Church of England Primary School we are committed in our aims to ‘Amaze, Excite and Inspire’ within the context of Christian belief and practice.  We strive to be an outstanding Church school, making a contribution to society at the heart of the community.

|  |  |
| --- | --- |
| **Area 1. To Maintain a Rigorous Culture of Highly Effective Safeguarding and Child Protection:**  | Amaze, Excite, Inspire*Jesus offers life in all its goodness***School crest 2.jpg** |
| **Area 2. To Further Develop The Quality of Education:**  |
| **Area 3: To Further Develop the Wider school programme** |
| **Area 4. To Further Develop the Christian Distinctiveness of the School** |
| **Area 5. To Further Develop Leadership at All Levels, Including, Governance** |

|  |
| --- |
| **Area for Improvement 1 – To Maintain a Rigorous Culture of Highly Effective Safeguarding and Child Protection** |
| **School Priority Target: (Intent)**Ensure all children are kept safe at all times.Ensure children understand how to keep themselves safe. |
| **Success Criteria**  |
| **Monitoring**WhoHowWhen | HT and Link governorSafeguarding auditTermly meetings | **Evaluation**WhoHowWhen | Governors evaluate effectiveness at S and P meetings each term |
| People Involved | All staffNominated safeguarding governor  | LA Monitoring | School Improvement Advisor (SIA) visits |
| **Pupil Voice** | Pupils involved in anti-bullying policy through school council and class discussions. |
| **Action (Implementation)** | **Lead Person**  | **Start/end date** | **How measured** | **Resources / Cost to school** |
| 1.1 | At the beginning of each school year instigate a timetabled safeguarding training/update session for each staff member on an annual basis to ensure that changes to both legislation and school policies are discussed and explained. This can be carried out on a team basis at an annual meeting or smaller update sessions at team meetings or on an ad hoc basis as new staff join the school.Whole school safeguarding training completed October 2019New staff have safeguarding training at inductionStaff meeting timetabled for mid year (9th March 2020)DSL and DDSL attend ongoing updates through the year and new information / changes fed back to staff following those sessions | RH | Early Sept 2019 | Checked by Nominated Safeguarding governor | DSL to deliver session/s to staff |
| 1.2 | Conduct peer review of safeguarding procedures and effectiveness with Lacock Primary and if required meet on a regular basis to discuss ongoing issuesEmail contact made between two governors | CS (LFPS) and FD (LPS) | ASAP | Progress reported at S&P meetings | None |
| 1.3 | Continue to monitor what safeguarding content is delivered to pupils and when – link to point 1.4 and 1.5 belowInformation gathered from staff – to be discussed with teachers at staff meeting in term 3 and feed into planning of wider curriculum | RH and CS | termly | Progress reported at S&P meetings | None |
| 1.4 | Monitor current PSHE curriculum to assess effectiveness and coverage in preparation for new requirementsNew curriculum Visit from HeartSmart (December 2019) who produce PSHE resources – investigating whether to take this on (cost £150 per year) | BD | Terms 1 – 3 | Reported at S and P meeting  | Subject leader time and staff meeting time |
| 1.5 | Develop and implement new PSHE / RSE scheme of work in preparation for new DfE requirements. (New formal title will be Relationships and Health Education – RHE)Ongoing | BD | By end of term 5 | Reported at S and P meeting | May need to purchase scheme of work and new resources depending on audit |
| 1.6 | Identify opportunities for visitors – NSPCC etc.Identify opportunities for visits – Life Skills / Junior Good Citizen etc.Dogs Trust | RH / BD | During the year | Reported at S and P meeting | Cost for transport or visitor charges. Parental contributions may be sought. |
| 1.7 | Revise / rewrite anti-bullying policy with children / staff and parents.School Council meetings led to a one page Anti-Bullying summary of main policy for pupils and parents. School councillors discussed with their classes.Anti bullying policy discussed with teaching staff and revised 26/ 11 20191.71 – share with parents | RH | November 2019 – during anti bullying week | S and P to approve revised policy | None |

|  |
| --- |
| **Area for Improvement 2: To Further Develop The Quality of Education** |
| **School Priority Target: (Intent) All subject leaders drive improvement in their subjects, so that children’s outcomes improve over time**Progress: The class average progress must be equal to or above national expectations |
| **Success Criteria:**Teaching is judged good or better by HT and LA advisor. Class data reports show satisfactory progress |
| **Monitoring**WhoHowWhen | HT and Link governorsTermly meetingsS and P meetings | **Evaluation**WhoHowWhen | Governors evaluate effectiveness at S and P meetings each term |
| People Involved | All staffLink governors | LA Monitoring | SIA visits |
| **Pupil Voice** | Pupils asked what they are learning, what their targets are, what they need to do next and how to make that improvement. |
| **Action** | **Lead Person**  | **End date** | **How measured** | **Resources/ Cost to school** |
| 2.1 | RE teaching – appoint subject leader; ensure RE curriculum meets SIAMS requirements.S/L is shared JO and RH – will need to be decided who is S/L from Sept 2020RE discussed with pupils – monitoring by Link Gov and HT – fed back to CD groupRE lesson obs to take place in term 3 and 4 | HT | Dec ‘19 | Link Gov / S&P | Understanding Christianity Package |
| 2.2 | S&P PPG funding review – ensure clear targeting and appropriate supportReport on website and discussed with LPSPG Report to be complete by end of Jan following discussion with HS in Dec 2019 | HT | Oct ‘19 | Link Gov |  |
| 2.3 | Based on expected or better progress, set % Targets for each cohort for attainment (based on prior attainment).*(Progress average pupil in the class makes expected progress or better)*At Appraisal meetings each teacher discussed their cohorts and set targets for expected attainment based on current attainment  | RH / JO | Oct ‘19 | Progress reported at S&P meetings |  |
| 2.3a | Identify how progress is demonstrated other than in iTrack data, esp. for SEN children who make smaller steps.Following discussion with Headteacher groups and LA advisors it is advised to consider each case individually – it is not possible to define for all children the steps they are expected to make | JO and teachers | Oct ‘19 | Reported at S and P meeting  |  |
| 2.4 | Develop Growth Mindset and positive pupil attitudes.Communicate with parentsNeeds more formal timing and higher profile – staff meetings and assemblies | JO | Throughout the year | Reported at S and P meeting |  |
| 2.5 | PPG focus at termly staff meetingsPPG | RH | Each term during the year | Reported at S and P meeting | 6 staff meetings |
| 2.6 | Lesson observations by subject leaders to judge quality of teaching and learningMaths took place in October 2019Good examples of reasoning and problem solving in all classes.English took place in January 2020Need to be reported at S and P | All subject leads | Throughout the year | Reported at S and P meeting | 1 release day per full time teacher in T1 and T6 |
| 2.7 | Maths Focus 1: preparation for implementation of MTC (multiplication check) | CC | During term 1 and 2 |  |  |
| 2.8 | Maths focus 2: Develop children’s use of concrete resources / pictorial representations moving to understanding of abstract concepts. | CC | Throughout the year |  |  |
| 2.9 | English focus 1: Spelling across the school | JN | Throughout the year |  |  |
| 2.10 | English focus 2: Further develop writing across the school to ensure all children make all possible progress. | JN | Throughout the year |  |  |

|  |
| --- |
| **Area for Improvement 3:** **To Further Develop the Wider school programme** |
| **School Priority Target: Support a sustainable, prioritised and broad programme of activity in line with new Ofsted Guidance**  |
| **Success Criteria:**Analysis of children’s subject input, with suggestions of any targeted ***rebalancing*** new OFSTED = broad and balancedIntegration of “11 things to do” into programme, with no increase in teacher workloadEffective / sustainable staffing |
| **Monitoring**WhoHowWhen | HT / S&P / FGBHT reportingTermly meetings |  |  |
| People Involved | All staff |  |  |
| **Pupil Voice** | Children’s views to feed into each point below through discussion of school council |
| **Action** | **Lead Person**  | **Start/end date** | **How measured** | **Resources / Cost to school** |
| 3.1 | Complete playground refurbishment, on time and to budgetGrass, netball court and posts both complete. | Finance Officer | Oct 19 | L&R | As agreed at L and R / FGB |
| 3.2 | Agreement of how the “11 things to do by 11” will be integrated into the programme.To include school council / Year 6 / staff meeting timeFinal list complete and ready to launch | HT | First S&P mtg | S&P | Staff meeting |
| 3.3 | Analysis of each subject ‘taught time’, with suggestions of any targeted rebalancing .Not complete – initial request for data and discussion with staff (Oct 2019) but topics mean subjects are taught in blocks through the year. TD day in Term 5 will address curriculum planning going forward (when class structure / pupil numbers will be clear) and ensure curriculum is well planned organised to skills and knowledge shown progression during the school.  | HT | By end of term 1 | S&P to FGB | Nil |
| 3.4 | Change to 3 data collections per year; demonstrating robust process and response (via subject leaders) to emergent issues / opportunitiesChange to three times per year and dates agreed for data collection to fit with S and P meetings. | HT | By end of term 1 | S&P | Nil |
| 3.5 | Enhance playtime provision:* MDSA training – complete and feedback given to JO after training
* Source additional playground resources – Major purchases discussed as part of SPG spend with Huw Solly, MDSA’s reminded to order / request smaller items.
* Discussion with school council – ongoing through the year
 | HT / JO | By end of Term 2 | Reported to S and P committee | Resources for playtimes – Sports Premium funding |
| 3.6 | Ensure pupils’ views are used through regular school council meetingsPupils’ views are collected – 11 by 11, parking issues, queues in toilets, house names – at council meetingsNot yet reported to S and P – need to ensure goes on agenda. | RH |  | Reported to S and P committee | Nil |
| 3.7 | Develop competitive sporting opportunities for younger children (Y4 and below)Not yet complete – most opportunities in local are for older children. Participation events take place (cross country run, multi skills) but not competitive. | RH / sports coaches |  | Reported to S and P committee | Transport costs through sport premium |
| 3.8 | Promote Wellbeing in school: Identify wellbeing lead among staff, follow DfE guidance on staff wellbeing. | JO / HW |  | Reported to S and P committee |  |

|  |
| --- |
| **Area for Improvement 4: To Further Develop the Christian Distinctiveness of the School** |
| **School Priority Target:**All statutory requirements are met.Christian distinctiveness is clear to school community |
| **Success Criteria**  |
| **Monitoring**WhoHowWhen | HT and foundation governorsTermly meetings | **Evaluation**WhoHowWhen | Governors evaluate effectiveness at S and P meetings. |
| People Involved | All staffChurch link – Katherine Bloomer | LA Monitoring | SIA visits |
| **Pupil Voice** | Worship council represent their classesChildren’s evaluations and feedback on Collective Worship |
| **Action** | **Lead Person**  | **Start/end date** | **How measured** | **Resources/ Cost to school** |
| 4.14.1a4.1b | Prepare for SIAMS 20/21: HT / Link Gov / KB attend training Refresh vision – approve at FGBTraining completed – need to feedback to staffVision has been re-written and shared with staff / governors, needs formal approval | -HT | Oct/Nov19 Mar20 | Christian Distinctiveness group meetings and Foundation governors  | £150 for SIAMS training |
| 4.2 | Develop Courageous Advocacy as part of the schools ongoing programmeWritten into 11 by 11Regular discussion at CD Group meetings – how to bring more into school life | HT | Dec 19 | Christian Distinctiveness group meetings and Foundation governors  |  |
| 4.3 | Implement new collective worship formatOpening and closing words used, candles and church calendar follow correct colours | HT | Sep 19 | Christian Distinctiveness group meetings and Foundation governors  |  |
| 4.4 | Ensure hall is appropriately set up and equipped for collective worshipHall set up correctly and regular reminders to look after the worship table | RH | Term 1 2019 | Christian Distinctiveness group meetings and Foundation governors |  |

|  |
| --- |
| **Area for Improvement 5:** Further develop leadership, including governance. |
| **School Priority Target:**All leaders (HT, AHT, SENCo, subject leaders) are clear in their roleAll staff understand the roles and responsibilities of leadersLeaders have clear and positive effect on pupil outcomes |
| **Success Criteria**  |
| **Monitoring**WhoHowWhen | HT and ChairTermly meetings | **Evaluation**WhoHowWhen | Governors evaluate effectiveness at S and P, L and R and FGB meetings. |
| People Involved | All staff | LA Monitoring | SIA visits |
| **Action** | **Lead Person**  | **Start/end date** | **How measured** | **Resources/ Cost to school** |
| 5.1 | Ensure that by end of academic year (July 2020) all school policies are updated, where required, and available to all staff on School Bus. | Clerk (plus all staff and governors) | Throughout the year | Relevant policies at S and P, L and R and FGB |  |
| 5.2 | Progressively implement the new Ofsted assessment regime of Intent, Implement and Impact, largely through the work of S&P to understand and evaluate the curriculum and monitoring tri-yearly performance improvement cycles.During the year the language of Intent / Implementation and Impact being introduced | HT and all staff and governors |  | S and P, L and R and FGB |  |
| 5.3 | Resolve the Headteacher’s employmentHT leaving at end of year, GB resolving future situation | CoG / HT | Feb 2020 | FGB |  |
| 5.4 | Related to the outcome of 5.3, refine our relationship with Lacock school. | CoG / HT | Feb 2020 | FGB |  |
| 5.5 | Ensure all staff are understand roles of leaders:James as AHTSubject leadersSENCo | RH / JO | End of term 1 | S and P committee |  |
| 5.6 | Develop subject annual tasks listComplete | RH | End of term 1 | S and P committee |  |
| 5.7 | All SEN procedures (to include identification, referral, monitoring) to be clear in light of new SENCo being employedDiscussed with staff during Term 1 and 2, staff meeting Jan 13th 2020 went through and confirmed all paperwork and processes for identification of SEN, records to be kept and referral to outside agencies.  | RH / SENCo | End of term 1 | S and P committee |  |

Notes for next SIP:

* Curriculum development from the ground up – look at principles for this school and how curriculum is organised to give the children the best chance at education. Include focus on foundation subjects, quality in all subjects, experiences other than the classrooms
* Governor monitoring – processes which enable what is happening, e.g. lesson observations, to be understood by governors